## Sheet1
Meeting Log: | Last updated: 02/15/2017 12:28 PM by Carlos
Date: | Purpose of Meeting: | Attendees: | Resolution: | Actions Required: | Additional Notes:
2017-01-24 | Discuss initial ideas from team members | Carlos, Courtnie, Lucas, Patrick | Will whittle down ideas to 5 before meeting again for in depth discussion | Carlos: Add Ideas to repository, create Google Form for voting; Everyone: Vote on google form(s) until we have a final 5 | Meeting with Dr. Wei 02/08/17, will meet sometime before then to choose at most 2 ideas to present
2017-01-26 | Select Project from list of 5, as narrowed down from the google form surveys | Carlos, Courtnie, Lucas, Patrick | Chose to turn in Fire Alarm and Teaching Assistant for Divide and Conquer - Initial Document due 2/3 | Please complete the following by 2/1: Carlos: Project Milestones; Courtnie: House of Quality, Engineering Specifications; Lucas: budget and financing, goals and objectives; Patrick: Project Block Diagram, Decision Matrix; | We decided to Use Fire Alarm and Teaching Assistant; See Deadlines spreadsheet for details;
2017-02-08 | Meet with Lei Wei, choose project, Assign research | Carlos, Courtnie, Lucas, Patrick | Chose Fire Alarm Project. See "Actions Required" for Research. | Please complete the following by 2/15: Carlos: Update Project Milestones; Courtnie: Update House of Quality; Lucas: goals and objectives; Patrick: Project Block Diagram; Complete by 2/22: Carlos: Smoke Sensors Research & Docs; Courtnie: Battery Research & Docs; Lucas: Microcontroller Research & Docs; Patrick: Wireless Communication Research & Docs; | Meeting Weekly on Wednesdays from now on
2017-02-15 | Discuss Updates for Initial Document/Proposal. Make sure everyone has Research Assigned, and Understands what is Required. | Carlos, Courtnie, Lucas, Patrick | Assigned Research for everyone. Will submit "Updates" documented by 2/16. | Please complete Research on at least one of the following by 2/22: Carlos: Smoke Sensors, Direction/Location Algorithm Research & Docs; Courtnie: Battery/Power Monitoring, Alarm System Components Research & Docs; Lucas: Microcontroller and Processor Research & Docs; Patrick: Wireless Communication Research and Processor & Docs; | Will look into sponsors later on in project. Add Software Flowchart to document whenever possible.